## Slide 1
Project Update: Q4 Onboarding & Billing
Onboarding rollout underway, billing migration delayed
Notes: Good morning. This deck covers the two main workstreams: the new onboarding flow and the billing provider migration. We'll walk through where each stands, who's driving, and what the December freeze means for our timeline.

## Slide 2
Onboarding rollout has begun
12%
of accounts now using the new onboarding flow behind a feature flag
2
Notes: We shipped the new onboarding flow behind a flag. So far 12% of accounts have it enabled. That gives us a real sample to validate behavior before we push it wider.

## Slide 3
Onboarding rollout: next steps
Monitor engagement and error rates for flagged accounts
Tom owns flag rollout and go/no-go decisions
Plan to increase flag percentage after initial data review
Any code not merged by Dec 8 waits until January
3
Notes: Tom is leading the flag rollout. We'll watch the data from the 12% cohort, then decide on expanding. The December 8th cutoff is firm — anything not merged by then sits until January.

## Slide 4
Billing migration slipped two weeks
2 weeks
delay due to a webhook mismatch between current and new provider
4
Notes: The billing provider migration was on track until we hit a webhook mismatch. That pushed the timeline back by two weeks. Sarah is working through the fix with the new provider's API docs.

## Slide 5
Billing migration: status & owner
Webhook mismatch identified and scoped
Sarah owns the billing workstream end to end
Fix in progress; target is to resolve before Dec 8 cutoff
If not merged by Dec 8, migration slips to January
5
Notes: Sarah is on payments and owns this workstream. She's scoped the webhook issue and is working on the fix. The December 8th freeze applies here too — if we miss that date, the migration waits until the new year.

## Slide 6
Workstream owners & status
ONBOARDING
Owner: Tom
12% of accounts live
Behind feature flag
Data review pending
BILLING
Owner: Sarah
Slipped 2 weeks
Webhook mismatch
Fix in progress
6
Notes: Two workstreams, two owners. Onboarding is live at small scale, billing hit a blocker. Both are racing the December 8th cutoff.

## Slide 7
December freeze: what it means
Any code not merged by Dec 8 is deferred to January
No deployments or releases after that date
Affects both onboarding expansion and billing migration
Team is prioritizing fixes to meet the cutoff
7
Notes: The December freeze is company-wide. Anything not merged by the 8th waits until January. That's the hard deadline for both workstreams.

## Slide 8
Risks to watch
Billing webhook fix may uncover additional mismatches
Onboarding data from 12% may show unexpected issues
Both workstreams compete for the same Dec 8 window
No buffer if either fix runs long
8
Notes: The main risk is the webhook fix could cascade. We also need to watch the onboarding data — 12% is small but enough to surface problems. With one cutoff for both, there's no slack.

## Slide 9
Immediate next steps
Tom: review onboarding data by end of week
Sarah: complete webhook fix and test
Both: confirm merge readiness by Dec 5
Team: decide on scope if only one workstream makes the cutoff
9
Notes: Tom reviews the onboarding data this week. Sarah finishes and tests the webhook fix. By December 5th we'll know if both can make the 8th, and if not, we'll decide which to prioritize.

## Slide 10
Next update: Dec 5
We'll report merge readiness for both workstreams
10
Notes: We'll reconvene on December 5th with a clear picture of what makes the cutoff and what defers to January. That's the next checkpoint.